## Dashboard
Metric | Total
Total Deposits Received | 33300
Total Earned Revenue | 20550
Total Unearned Revenue (Liability) | 12750
Average % Completion | 63.33%
Number of Active Jobs | 2
Jobs Fully Earned (Completed) | 1

## Unearned_Revenue_Calculator
Project Name | Client Name | Contract Total ($) | Deposit Received ($) | Deposit Date | % Complete | Earned Revenue ($) | Unearned Revenue Remaining ($) | Revenue Recognized to Date ($) | Remaining Contract Balance ($) | Job Status | Notes
Office Renovation Electrical Upgrade – Harborview Financial | Harborview Financial Services | 36000 | 10800 | 2025-08-01 | 100% | 10800 | 0 | 36000 | 0 | Completed | Final inspection passed on 10/18/2025; client paid in full. All revenue recognized.
Lighting Retrofit – Apex Distribution Center | Apex Logistics Group | 25000 | 7500 | 2025-09-10 | 50% | 3750 | 3750 | 12500 | 12500 | In Progress | Awaiting client approval for change order; materials delay pushed completion to Q1 2026.
Rooftop HVAC Replacement – Riverside Office Complex | Riverside Property Management, LLC | 45000 | 15000 | 2025-09-20 | 40% | 6000 | 9000 | 18000 | 27000 | In Progress | 40% of mechanical installation complete. Next progress billing scheduled at 60% completion.

## Instructions
How to Use This Calculator:
1. Enter each new job on a separate line.
2. Record the deposit amount in column D when received.
3. Update % Complete (column F) each time you hit a major milestone or billing stage.
4. The sheet automatically calculates how much of that deposit has been earned and how much remains unearned.
5. Review your Dashboard monthly to ensure your unearned revenue liability aligns with your accounting software.
Key Terms:
Unearned Revenue: Money you’ve been paid but haven’t earned yet.
Earned Revenue: The portion of that deposit tied to completed work.
% Complete: The best estimate of how much work has been done — can be based on milestones or time.
Liability: What you owe your customer until the work is done.